## Progress Tracker
Ref | Level | Section | Page Name |  | URL | Priority | Content | Design | Development | Review | % Complete | Owner | Target Live Date | Notes
1.0 | 0 | Home | Home |  | / | P1 | Not started | Not started | Not started | Not started | 0% |  |  | Hero direction still open: real warehouse vs product-first UI.
2.0 | 1 | Solutions | Solutions Hub |  | /solutions | P1 | Not started | Not started | Not started | Not started | 0%
2.1 | 2 | Solutions | Rack Safety and Intelligence |  | /solutions/rack-intelligence | P2 | Not started | Not started | Not started | Not started | 0% |  |  | Powered by IRDS.
2.2 | 2 | Solutions | MHE Safety and Productivity |  | /solutions/mhe-intelligence | P2 | Not started | Not started | Not started | Not started | 0% |  |  | Powered by MEPS and RTSS.
2.3 | 2 | Solutions | Inventory Intelligence |  | /solutions/inventory-intelligence | P2 | Not started | Not started | Not started | Not started | 0%
2.4 | 2 | Solutions | Warehouse Execution |  | /solutions/warehouse-execution | P2 | Not started | Not started | Not started | Not started | 0% |  |  | Powered by ATOS.
2.5 | 2 | Solutions | MHE Diagnostics and Maintenance |  | /solutions/mhe-diagnostics | P2 | Not started | Not started | Not started | Not started | 0% |  |  | Powered by IMDS.
2.6 | 2 | Solutions | Management Intelligence |  | /solutions/management-intelligence | P2 | Not started | Not started | Not started | Not started | 0% |  |  | Powered by AIMS.
3.0 | 1 | Platform | Platform Hub |  | /platform | P2 | Not started | Not started | Not started | Not started | 0%
DIGITAL TWIN
3.1 | 2 | Platform | MEPS |  | /platform/overview | P3 | Not started | Not started | Not started | Not started | 0%
3.3 | 2 | Platform | IRDS |  | /platform/digital-twin | P3 | Not started | Not started | Not started | Not started | 0%
3.4 | 2 | Platform | ATOS |  | /platform/ai-operational-intelligence | P3 | Not started | Not started | Not started | Not started | 0%
3.5 | 2 | Platform | RTSS |  | /platform/execution-engine | P3 | Not started | Not started | Not started | Not started | 0% |  |  | ATOS.
3.6 | 2 | Platform | IMDS |  | /platform/integrations | P3 | Not started | Not started | Not started | Not started | 0% |  |  | WMS, ERP, CCTV, RFID, MHE, maintenance, APIs.
3.7 | 2 | Platform | AIMS |  | /platform/security | P3 | Not started | Not started | Not started | Not started | 0% |  |  | Footer Security link points here.
4.0 | 1 | Hardware | Hardware Hub |  | /hardware | P1 | Not started | Not started | Not started | Not started | 0%
4.1 | 2 | Hardware | AI Vision Camera System |  | /hardware/ai-vision | P1 | Not started | Not started | Not started | Not started | 0% |  |  | Standalone or platform connected.
AI Vision Pro
AI Vision Ultra
AI Vision Max
4.2 | 2 | Hardware | OmniBox Edge Processors |  | /hardware/omnibox | P2 | Not started | Not started | Not started | Not started | 0% |  |  | Four roles: Edge, AI, Motion, Core.
OmniBox Edge
OmniBox AI
OmniBox Motion
OmniBox Core
4.3 | 2 | Hardware | RTLS and Location Intelligence |  | /hardware/rtls | P2 | Not started | Not started | Not started | Not started | 0% |  |  | LiDAR-first. Needs a Pilot Stage badge.
LiDAR
Wifi
Bluetooth
UWB
4.4 | 2 | Hardware | Sensor Stack |  | /hardware/sensor-stack | P3 | Not started | Not started | Not started | Not started | 0% |  |  | Covers all four sensors. Not separate pages.
Access Control
Crash Monitoring System
Speed Monitoring System
Location Monitoring System
Pallet Detection Sensor
Battery Management System
4.6 | 2 | Hardware | Guided Inspection Systems | Coming Soon | URL TBC | P3 | Not started | Not started | Not started | Not started | 0% |  |  | BLOCKED. AirScan and FloorScan have no nav placement or URL yet.
AirScan
Floor Scan
5.0 | 1 | Services | Services Hub |  | /services | P1 | Not started | Not started | Not started | Not started | 0%
5.1 | 2 | Services | Rack Inspection Services |  | /services/rack-inspection | P1 | Not started | Not started | Not started | Not started | 0% |  |  | Most requested service.
5.2 | 2 | Services | Structural Verification |  | /services/structural-verification | P2 | Not started | Not started | Not started | Not started | 0%
5.3 | 2 | Services | Inventory Reconciliation and Audit |  | /services/inventory-audit | P2 | Not started | Not started | Not started | Not started | 0%
5.4 | 2 | Services | MHE Productivity Assessment |  | /services/mhe-productivity-assessment | P2 | Not started | Not started | Not started | Not started | 0%
5.5 | 2 | Services | Safety and Operational Assessment |  | /services/operational-assessment | P3 | Not started | Not started | Not started | Not started | 0%
5.6 | 2 | Services | Deployment and Support |  | /services/deployment-support | P3 | Not started | Not started | Not started | Not started | 0%
6.0 | 1 | Industries | Industries |  | /industries | P2 | Not started | Not started | Not started | Not started | 0%
6.1 | 2 | Industries | Warehousing and Distribution |  | /industries/warehousing-distribution | P3 | Not started | Not started | Not started | Not started | 0% |  |  | URL proposed.
6.2 | 2 | Industries | Third-Party Logistics (3PL) |  | /industries/third-party-logistics | P3 | Not started | Not started | Not started | Not started | 0% |  |  | URL proposed.
6.3 | 2 | Industries | E-commerce |  | /industries/ecommerce-fulfilment | P3 | Not started | Not started | Not started | Not started | 0% |  |  | URL proposed.
6.4 | 2 | Industries | Cold Storage |  | /industries/cold-storage | P3 | Not started | Not started | Not started | Not started | 0% |  |  | URL proposed.
6.5 | 2 | Industries | Manufacturing |  | /industries/manufacturing | P3 | Not started | Not started | Not started | Not started | 0% |  |  | URL proposed.
6.6 | 2 | Industries | Automotive |  | /industries/automotive | P3 | Not started | Not started | Not started | Not started | 0% |  |  | URL proposed.
6.7 | 2 | Industries | FMCG |  | /industries/fmcg | P3 | Not started | Not started | Not started | Not started | 0% |  |  | URL proposed.
6.8 | 2 | Industries | Food and Beverage |  | /industries/food-beverage | P3 | Not started | Not started | Not started | Not started | 0% |  |  | URL proposed.
6.9 | 2 | Industries | Pharmaceuticals |  | /industries/pharmaceuticals | P3 | Not started | Not started | Not started | Not started | 0% |  |  | URL proposed.
|  | Industries | Retail
|  | Industries | Chemical
|  | Industries | Aviation Logistics
|  | Industries | Heavy Equipment
|  | Industries | Industrial Machinery
|  | Industries | Industrial Tech
|  | Industries | Renewable Energy
|  | Industries | Building Materials
|  | Industries | Fashion Retail
|  | Industries | Health Care
7.0 | 1 | Resources | Resources Hub |  | /resources | P2 | Not started | Not started | Not started | Not started | 0%
7.1 | 2 | Resources | Case Studies |  | /resources/case-studies | P3 | Not started | Not started | Not started | Not started | 0% |  |  | URL proposed.
7.2 | 2 | Resources | News Room |  | /resources/insights | P3 | Not started | Not started | Not started | Not started | 0% |  |  | URL proposed.
7.3 | 2 | Resources | Videos |  | /resources/videos | P3 | Not started | Not started | Not started | Not started | 0% |  |  | URL proposed.
7.4 | 2 | Resources | Glossary (Industry Compliance Guides) |  | /resources/compliance-guides | P3 | Not started | Not started | Not started | Not started | 0% |  |  | URL proposed.
7.5 | 2 | Resources | White Papers |  | /resources/white-papers | P3 | Not started | Not started | Not started | Not started | 0% |  |  | URL proposed.
7.6 | 2 | Resources | Technical Notes |  | /resources/technical-notes | P3 | Not started | Not started | Not started | Not started | 0% |  |  | URL proposed.
7.7 | 2 | Resources | Downloads |  | /resources/downloads | P3 | Not started | Not started | Not started | Not started | 0% |  |  | URL proposed.
7.8 | 2 | Resources | Frequently Asked Questions (FAQs) |  | /resources/faqs | P3 | Not started | Not started | Not started | Not started | 0% |  |  | URL proposed.
|  | Resources | Events
|  | Resources | Blogs
|  | Resources | Industry Reports
8.0 | 1 | Company | Company Hub |  | /company | P3 | Not started | Not started | Not started | Not started | 0%
8.1 | 2 | Company | About RAMS |  | /company/about | P3 | Not started | Not started | Not started | Not started | 0% |  |  | URL proposed.
8.2 | 2 | Company | Leadership |  | /company/leadership | P3 | Not started | Not started | Not started | Not started | 0% |  |  | URL proposed.
8.3 | 2 | Company | Customers |  | /company/customers | P3 | Not started | Not started | Not started | Not started | 0% |  |  | URL proposed.
8.4 | 2 | Company | Certifications and Security |  | /company/certifications | P3 | Not started | Not started | Not started | Not started | 0% |  |  | URL proposed.
8.5 | 2 | Company | Partners |  | /company/partners | P3 | Not started | Not started | Not started | Not started | 0% |  |  | URL proposed.
8.6 | 2 | Company | Careers |  | /company/careers | P3 | Not started | Not started | Not started | Not started | 0% |  |  | URL proposed.
8.7 | 2 | Company | Contact Us |  | /company/contact | P3 | Not started | Not started | Not started | Not started | 0% |  |  | URL proposed.
|  | Company | Global Impact
|  | Company | Awards & Recognition
Accessibilty
10.1 | 1 | Conversion | Find Your Starting Point | CTA | /find-your-starting-point | P1 | Not started | Not started | Not started | Not started | 0% |  |  | Three-step guided selector.
10.2 | 1 | Conversion | Book a Demo | CTA | /book-a-demo | P1 | Not started | Not started | Not started | Not started | 0% |  |  | Keep the form short.
10.3 | 1 | Conversion | Platform Login | for Dashboard | External | P3 | Not started | Not started | Not started | Not started | 0% |  |  | Visually secondary to the CTAs.
11.1 | 1 | Footer | Privacy Policy |  | /privacy-policy | P2 | Not started | Not started | Not started | Not started | 0% |  |  | Legal review required.
11.2 | 1 | Footer | Terms of Use |  | /terms-of-use | P2 | Not started | Not started | Not started | Not started | 0% |  |  | Legal review required.
11.3 | 1 | Footer | Cookie Policy |  | /cookie-policy | P2 | Not started | Not started | Not started | Not started | 0% |  |  | Legal review required.
11.4 | 1 | Footer | Responsible AI Statement |  | /responsible-ai | P2 | Not started | Not started | Not started | Not started | 0% |  |  | Legal review required.
Social media icons
Help
Certifications and Security
|  |  | About Us | Short
|  |  | Email ID | connect@rams.digital
|  |  | Phone no. | Marketing
Site Map
WhatsApp Business Chat
Chat Bot
Note on D11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Change URLs
Note on E20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: add PPE detection in features Reply: face authentication

## How to use
How to use this tracker
What you update
Content, Design, Development, Review | Four dropdowns per page: Not started, In progress, Blocked, Complete. These are the only cells you normally change.
Owner | Who is accountable for that page.
Target Live Date | Planned publication date.
Priority | P1 launch, P2 phase two, P3 later. Dropdown.
What calculates itself
% Complete | Counts how many of the four stages say Complete, divided by four. One stage done shows 25 percent, all four shows 100 percent. Do not type over it.
Dashboard tab | Every number reads from the tracker. Change a dropdown and the dashboard moves.
Colours
Green | Complete.
Amber | In progress.
Red | Blocked.
Orange row | A page with an unresolved structural decision.
Grey bold row | A top-level tab or hub page.
Open decision
Guided Inspection Systems | AirScan and FloorScan have no navigation placement and no URL. Resolve before the Hardware section can be finished.

## Dashboard
RAMS 2.0 Website - Build Progress
Every figure is a live formula. Update the Progress Tracker tab and this recalculates.
Overall completion
Total pages | 79
Pages fully complete | 0
Pages started but not finished | 0
Pages not started | 62
Overall site progress | 0%
Progress by stage
Stage | Complete | In progress | Blocked | Not started
Content | 0 | 0 | 0 | 62
Design | 0 | 0 | 0 | 62
Development | 0 | 0 | 0 | 62
Review | 0 | 0 | 0 | 62
Progress by section
Section | Pages | Complete | Progress
Home | 1 | 0 | 0%
Solutions | 7 | 0 | 0%
Platform | 7 | 0 | 0%
Hardware | 6 | 0 | 0%
Services | 7 | 0 | 0%
Industries | 20 | 0 | 0%
Resources | 12 | 0 | 0%
Company | 10 | 0 | 0%
Campaign | 0 | 0 | 0%
Conversion | 3 | 0 | 0%
Footer | 4 | 0 | 0%
Progress by priority
Priority | Pages | Complete | Progress
P1 | 8 | 0 | 0%
P2 | 18 | 0 | 0%
P3 | 36 | 0 | 0%
Blockers
Stages currently marked Blocked | 0
Known open decision: Guided Inspection has no nav placement or URL.